## Sheet1
Week | Start Date | Milestone / Task | Status
Week 1 | 2025-01-15 | • Discussion on initial project ideas with professor • Brainstormed potential capstone directions • Decided to build a car diagnostic and reverse engineering tool based on CAN_Commander | Completed
Week 2 | 2025-01-22 | • Began researching how CAN bus communication works in vehicles • Explored how diagnostic tools and reverse engineering are done using CAN • Looked into how ESP32 can be used with a CAN Bus shield • Took initial notes on what features we might include in our own version | Completed
Week 3 | 2025-01-29 | • Started planning how to break the project into clear development phases • Outlined key features the system should have (CAN message reading, sending, filtering, logging, etc.) • Researched what hardware components are needed for the project (CAN Bus shield, ESP32 compatibility, connectors, power supply, etc.) • Explored compatible CAN transceivers and shielding options • Looked into useful tools like Serial Monitor, multimeter, and possible simulators for safe testing • Documented potential hardware challenges (e.g., voltage compatibility, wiring issues) and how to approach them | Completed
Week 4 | 2025-02-05 | • Finalized hardware choices by comparing CAN transceivers and CAN Bus shield specs • Verified compatibility with ESP32 in terms of voltage, pin configuration, and connections • Researched CAN libraries and message structures for ESP32 • Chose PlatformIO with VS Code as the primary development environment • Explored open-source tools for CAN diagnostics and testing • Compiled a detailed list of all hardware and software components needed for the project | Completed
Week 5 | 2025-02-12 | • Completed final review of required hardware and software tools • Chose compatible CAN Bus shield, transceiver, and supporting components • Confirmed compatibility with ESP32 (voltage levels, pin mapping, etc.) • Finalized development environment: PlatformIO with VS Code • Placed orders for all necessary hardware parts to begin physical setup | Completed
Week 6 | 2025-02-19 | • Created and submitted a rough sketch of the project layout to the professor • Continued researching CAN communication and project implementation methods • Refined understanding of how different components will interact | Completed
Week 7 | 2025-02-26 | • Created a flow diagram outlining the system’s overall operation • Finalized and submitted the functional requirements document • Refined how different modules (receiving, sending, filtering) will interact in the system | Completed
Week 8 | 2025-03-05 | SPRING BREAK | Break
Week 9 | 2025-03-12 | • Successfully connected the OBD-II interface to the ESP32 • Used a custom CAN shield with built-in regulation to manage communication • Soldered a header pin to the custom board to interface with the ESP32 • Verified physical setup and prepared for CAN data testing | Completed
Week 10 | 2025-03-19 | • Met with professor to discuss current progress and upcoming tasks • Planned to test the hardware setup and debug any communication issues • Outlined goals to begin CAN data transmission development • Started working on a weekly milestone timeline to track progress throughout the semester | Completed
Week 11 | 2025-03-26 | • Finalized and submitted a detailed weekly milestone timeline for the project • Structured the timeline based on key phases: planning, setup, development, testing, and presentation • Shared the timeline with professor to align on expectations and deliverables • Used the timeline to guide upcoming weekly tasks and track progress | Completed
Week 12 | 2025-04-02 | • I will learn how to use PlatformIO with the ESP32 • I will test simple ESP32 programs to understand how uploading and debugging works • I will install the CAN libraries and try a basic CAN receive sketch • I will prepare the setup for testing CAN communication | Completed
Week 13 | 4/92025 | Create GitHub repository for the project to start tracking progress. Begin programming and testing the tool (currently in the testing phase). Log raw CAN messages to the serial monitor for further debugging and improvements. | Completed
Week 14 | 2025-04-16 | Continue programming the tool and debug existing features. Test and refine message filtering by CAN ID. Start implementing OBD-II parameter extraction (e.g., RPM, speed). | Completed
Week 15 | 2025-04-23 | Finalize basic functionality (CAN sniffer, filtering, OBD-II). Update GitHub with all code and documentation. Prepare a roadmap for Fall semester tasks (security features, GUI, etc.). | Completed
|  | SUMMER BREAK | Break
|  | SUMMER 2025 CLASS STARTS | New Semester
Week 1 | 2025-05-21 | Review project progress from the Spring semester. Finalize basic functionality (CAN sniffer, message filtering, OBD-II). Update GitHub repository with any last-minute changes and document the status. | Completed
Week 2 | 2025-05-28 | Project paused due to personal emergency | Completed
Week 3 | 2025-06-04 | Project paused due to personal emergency | Completed
Week 4 | 2025-06-11 | Start using SavvyCAN to read live CAN data from ESP32. Try to find useful signals like RPM and speed. Make a basic plan or sketch for how to show this data on a screen. | Completed
Week 5 | 2025-06-18 | Start writing code for the ESP32 to read data from the car’s system Focus on getting basic values like RPM and speed from the CAN Bus Organize the code so it’s clean and easy to work with later | Completed
Week 6 | 2025-06-25 | Work on decoding the data so the tool can show correct values Begin learning how to detect basic car problems (using error codes or unusual values) Test with simulated car data using software like SavvyCAN | Completed
Week 7 | 2025-07-02 | Add logic to identify faulty or abnormal values (e.g., RPM too high, no signal) Prepare to read Diagnostic Trouble Codes (DTCs) if possible Clean up the code so it can handle real-world car data without crashing | Completed
Week 8 | 2025-07-09 | Design a simple display or interface to show RPM, speed, and any car warnings Show diagnostic messages clearly — like “Engine Running Fine” or “Check RPM Sensor” Work on saving the data or displaying it in a useful way (terminal, screen, or webpage) | Completed
Week 9 | 2025-07-16 | Integrate basic diagnostic logic: add checks for missing or abnormal CAN data (e.g., no RPM signal, out-of-range speed), and display simple messages to indicate possible issues. | Completed
Week 10 | 2025-07-23 | Perform final end-to-end testing of all features (CAN message reading, OBD-II decoding, error detection, simulated data injection). Ensure the tool works smoothly and shows accurate outputs. Prepare final project report, code documentation, and user guide for submission. | Completed
Week 11 | 2025-07-29 | Polish slides Practice Q&A Present on July 29, 2025 | Completed
Week 12 | 2025-08-06 | Presentation Day | PENDING